## Green
Dissertation Project Management
Dissertation Plan
Ciaran Downes
Project start date: | 2021-04-26 | [10 empty] | Scrolling increment: | [5 empty] | 38
Milestone marker: | 1 | 1 |  |  | June | [27 empty] | July
 | time axis 2021-06-03 to 2021-07-28
Milestone description | Notes | Progress | Start | Days | time axis 2021-06-03 to 2021-07-28
Introduction & Literature Review
Project proposal for first supervisor meeting | Aim/Objective | 100% | 2021-04-26 | 7
Topic reading and note-taking | General | 100% | 2021-04-26 | 21
Introduction plan and draft |  | 100% | 2021-05-04 | 10
Literature review plan and draft |  | 100% | 2021-05-14 | 18
Review progress with supervisor | MS Teams | 100% | 2021-05-18 | 1
Portfolio modelling
Meeting with supervisor | MS Teams | 100% | 2021-06-01 | 1
Data collection | Eikon | 100% | 2021-06-01 | 5
Review progress with supervisor | MS Teams | 100% | 2021-06-22 | 1 | bar: 2021-06-22
Portfolio optimisation and backtest | Bottleneck | 100% | 2021-06-07 | 40
Review progress with supervisor | MS Teams | 100% | 2021-06-29 | 1 | bar: 2021-06-29
Processing results
Methodology plan and draft |  | 100% | 2021-06-29 | 10
Review progress with supervisor | MS Teams | 100% | 2021-07-06 | 1 | bar: 2021-07-06
Produce data visualisations |  | 100% | 2021-07-01 | 5
Produce results tables |  | 100% | 2021-07-07 | 3
Analyse results |  | 100% | 2021-07-07 | 3
Finalising & Submission
Results & Discussion plan and draft |  | 100% | 2021-07-12 | 7
Submit first draft to supervisor |  | 100% | 2021-07-19 | 1 | bar: 2021-07-19
Receive final feedback from supervisor |  | 100% | 2021-07-23 | 1 | bar: 2021-07-23
Implement necessary changes |  | 100% | 2021-07-23 | 6
Final review |  |  | 2021-07-28 | 2
Submission | Completed |  | 2021-07-30 | 1